## Sheet1
Risk Assessment for Hirers of HEC venues - Marana Auditorium and Civic Theatre |  | D13/113384
Task /area of venue | Identified risks | Risk Rating |  |  | Controls |  | Responsibility
| (please see examples below) | How severe / how likely? |  |  | (how the risk may be managed) |  | Carol Whittaker
|  | Please refer to Risk Rating Chart 3.2.10 |  | D11/32927
|  | Likelihood | Consequence | Risk Ranking
Transporting of performers to venues | Local traffic congestion | 2D | 2D | 2D | Member of Volunteer |  | Carol Whittaker
Movement of performers between/ around venues | Tripping, falling | 2C | 2D | 2D | Studio Teachers / Parents |  | Carol Whittaker
Supervision of performers at venues | Performers missing or injured | 2C | 2D | 2D | Studio Teachers / Parents |  | Carol Whittaker
Moving furniture | Injury sustained from not seeking assistance | 1E | 1E | 1E | No one will be moving furniture |  | Carol Whittaker
(minimum 2 person lift)
Delivering props and other large items | Injury sustained from not seeking assistance | 2D | 3C | 3C | Studio's & Parents are responsible for |  | Anit McMillan
| (minimum 2 person lift) |  |  |  | loading in and out of the venue
Access to stage and back of stage areas | Change in floor levels; dark unlit areas - trip hazard | 2E | 3C | 3C | Will have torches backstage, |  | Carol Whittaker
ensure no objects are in the way
Access to dressing rooms | Large gaps in handrails on access stairs - fall hazard | 2D | 3M | 2L | Stair Monitor |  | Anita McMillan
Access to Dress Circle | Low railing at front of dress circle | 2D | 3H | 2M | No children allowed without an Adult |  | Karen Argyropoulos
Operation of HEC equipment by 3rd parties - follow spots, comms side of stage, fly bars | Damage to equipment | 1E | 1E | !E | will not be working fly bars or follow |  | Carol Whittaker, Anita McMillan
| Electrocution |  |  |  | spots,
Venue provides training for comms
Parking facilities at venues | Traffic hazard | 1D | 1D | 1D | Beyond our | our control / council carpoark | Duty Manager ?
Exiting venues | Crowd build up | 1D | 2D | 2D | Have programmed our event to |  | Carol Whittaker, Anita McMillan
minimise crowd buildup
Loading dock | Absence of lift - stairs only | 1D | 1D | 1D | minimum traffic at dock |  | Anita McMillan
Emergencies | No immediate access to first aid | 1E | 1C | 3E | We have full First Aid Kit backstage and |  |  | Karen Argyropoulos
Client has not noted duty officer's number in the event of emergency 0411 743 258 | Duty officer is in another venue at time of emergency |  |  |  | in the Auditorium + addition ice packs |  |  | Duty Manager
Client has not advised their guests of emergency procedures | Evacuation of venue required and client is not in |  |  |  | We have first aid qualified volunteers |  |  | Anita McMillan
| attendance at venue |  |  |  | Client will always be in attendance at |  |  | Carol Whittaker
[5 empty] | Venue. | We will address audience re evacuation
Use of amenities | Slippery floor from water spillage | 1C | 2C | 3C | Signage will be displayed, monitoring |  |  | Anita McMillan
cleanliness and reporting any hazards
Understage area | Low ceiling | 1D | 1D | 1D | Competitors are Supervised and |  |  | Carol Whittaker / Anita McMillan
| Trip hazard (storage area) |  |  |  | nominated Dance School Reps
Marana goods lift | Getting stuck if doors jam | 1E | 1E | 1E | This lift is not used by our Event |  | N/A
No phone in lift
Gap between lift floor and floor level
Walk through between Marana and loading dock | Possibility of slippery floor if wet | 1E | !D | 1D | If raining will be supervised and water |  | Michelle Cameron
will be mopped up ASAP
Egress from front of stage via steps | No railing | 1E | 1E | 1E | This stairs will not be used by |  | Carol Whittaker
Competitors or Audience Members
Furniture placed in foyer areas | Limited egress for emergency evacuation | 1E | 1E | 1E | We do not require furniture in Foyer |  | Duty Manager
Venue open during performance | Members of public can gain access to event | 1E | 1E | 1E | Only those competiing and parents |  | Sandra McKenzie
will be entering the Venue (no GP)
Client supplying food and beverages but has not informed venue | Bump in and bump out times and catering / RSA | 1E | 1E | 1E | not required |  | N/A
Protocols and compliance requirements not discussed
prior to event
Client supplying back drops for event but has not informed venue | Fire risk associated with non fire retardent materials | 1E | 1E | 1E | N/A |  | N/A
Client has not advised of attendees in wheel chairs | Special seating not pre arranged in floor plan; | 1C | 1C | 1C | Chairs are movable and will |  | Michelle Cameron
| Access to venue not discussed prior |  |  |  | accommodate any special needs